## Project Gantt Chart Template
PROJECT: Tick-King Gannt Chart
Project Manager: Nolan Brown
ACTIVITY PLAN
| WEEK > |  |  |  |  | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9
# | Activity |  |  | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
1 | PROJECT MANAGEMENT | 2022-09-18 | 2022-12-04 | 1 | 78 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | PROTOTYPE DESIGN | 2022-09-21 | 2022-12-04 | 4 | 78 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Review conceptual design | 2020-06-01 | 2020-06-05 | -838 | -834
4 | Check compliance of all parts and their availability | 2020-06-08 | 2020-06-10 | -831 | -829
5 | Final Design Approval | 2022-09-18 | 2022-09-23 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1
6 | PRODUCTION CREATION (CODE) | 2022-09-23 | 2022-12-04 | 6 | 78 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Server and Client set up | 2022-09-26 | 2022-10-02 | 9 | 15 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | Log In Front End | 2022-09-26 | 2022-10-02 | 9 | 15 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Create Account Page | 2022-09-26 | 2022-10-02 | 9 | 15 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | Home Screen | 2022-09-24 | 2022-11-02 | 7 | 46 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 | To-Do List | 2022-09-25 | 2022-11-02 | 8 | 46 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | Create Study Sets | 2022-09-24 | 2022-11-02 | 7 | 46 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | Connect With Other Students | 2022-09-24 | 2022-12-01 | 7 | 75 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14
15
16
17
18
19
20
21
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
|  | Total (hrs) | MANPOWER |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
|  | 47 | Project Manager (Nolan) |  |  | 1 | 1 | 1 | 1 | 4 |  |  | 1 | 1 | 1 | 1 | 4 |  |  | 1 | 1 | 1 | 1 | 4 |  |  | 1 | 2 | 2 | 2 | 4 |  |  | 2 | 2 | 2 | 2 | 4
|  | 64 | Scrum Master (Lydia) |  |  | 1 1: 8; 2 2: 8; 3 3: 8; 4 4: 8; 5 5: 8; 9 9: 8; 10 10: 8; 11 11: 8
|  | 80 | Software Dev (Luke) |  |  | 8 8: 8; 9 9: 8; 10 10: 8; 12 12: 8; 15 15: 8; 16 16: 8; 17 17: 8; 18 18: 8; 19 19: 8; 22 22: 8
|  | 144 | Software Dev (Vinny) |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 |  | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
|  | 23 | Software Dev (Bryan) |  |  | 23 23: 8; 24 24: 8; 25 25: 1; 26 26: 1; 29 29: 1; 30 30: 1; 31 31: 1; 32 32: 1; 33 33: 1
|  | 0 | Quality Manager
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Hey @Bryan Banuelos Can you rename the document for our project? Thanks!

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com